## Engagement Info
GD - Program Management Edge - Aug 11-20, 2026
Reconciled reference. Source of truth = client-confirmed Logistics Form (docx). See 'Reconciliation Notes' tab.
Field | Detail
Engagement | Program Management Edge (Program Management Simulation)
Client | General Dynamics - Progeny Systems (GDMS)
Dates | August 11-20, 2026
Setup | Monday, August 10, 2026 - 1:00 PM to 5:00 PM
Daily hours | 8:30 AM - 4:30 PM EST [!] internal tracker previously said 8:00-4:00 - verify
Venue | General Dynamics Progeny Systems 9100 Ashton Ave, Manassas, VA 20110 Room: USS Groton Conf Room, Building 3
Instructor | Dr. Dale Christenson - dale@pmcoe.ca - 250-217-5362
Support / Observe | Emil Tarka
Attendees | 24 - Room setup: 6 team pods of 4 - Roster: not required by client
Certificates | No
Evaluation | GD internal evaluation system (Tarka online eval not used)
AV / IT | Wall-mounted screens; Clickshare + hard-wired HDMI; share screen via Teams (Groton has its own Teams account, touch screen at back). Instructor uses own laptop. Wi-Fi available but download materials beforehand - poor cell service. Onsite IT: Brandon Dowdy.
Ship materials to | Attn: Jill Jule General Dynamics Progeny Systems 9100 Ashton Ave, Manassas, VA 20110 [!] NOT the Pittsfield, MA address in the old tracker
Invoice to | Rachel Hawthorne - Rachel.Hawthorne@gd-ms.com (email OK)
Airports | Dulles Intl (IAD) or Reagan National (DCA)
Hotels | Residence Inn Manassas Battlefield Park (10 min) - Courtyard Manassas Battlefield Park (15 min) - Westfields Marriott Washington Dulles (20 min)
Key Contacts
Contact | Role / details
Bart Turrano | Course coordinator - Bart.Turrano@gd-ms.com
Amber Dean | Alternate contact - Amber.Dean@gd-ms.com - 413-664-1210 (tracker also lists 413-449-7139 - verify)
Jill Jule | Site contact / ship-to - Jill.Jule@gd-ms.com - (571) 370-7495
Rachel Hawthorne | Invoicing - Rachel.Hawthorne@gd-ms.com
Brandon Dowdy | Onsite IT support
Deena Shipman | Uploading security clearance material (confirm status)
Eric | Tarka - compiling course materials list and printing/shipping
Kim | Tarka - confirming attendance-reporting approach with Emil

## Task Tracker
Task Tracker - reconciled
Task | Details | Owner | Target date | Status
Instructor confirmed | Dr. Dale Christenson leads; Emil Tarka observes and supports. | Tarka |  | Confirmed
Onsite / in-person class | Held at GD Progeny Systems, Manassas VA (Bldg 3, USS Groton room). | - | Aug 11-20 | Confirmed
Request roster / logistics | Send logistics sheet to Bart. | Emil | 2026-06-15 | Done
Completed logistics form | Send completed Logistics Request form to Dr. Dale so he can arrange travel and site access. (Form is COMPLETE.) | Emil | 2026-06-20 | Done
Roster and QR code | Send roster to Dale. | Emil | 2026-07-20 | Open
Course list | Eric to provide detailed list of materials required, including printing. | Eric |  | In Progress
Classroom access | Venue confirmed (Manassas). GDMS site - security clearance still to be confirmed. | Bart / Emil | 2026-07-01 | Confirm
Classroom arrangement | AV as needed; 6 team pods of 4. Emil and Dale arrive to set up the room. | Emil / Dale | 2026-08-10 | Scheduled
Security access | Deena Shipman uploading security material - confirm complete before arrival. | Deena |  | Confirm
Course materials (printed) | Manuals (28) + handouts via Mimeo - sent to Eric to compile and ship. Name tents, case studies, charts already done. | Eric / Mimeo | 2026-07-01 | In Progress
Materials (non-printed) | FFMBAs, lanyards, duotangs, ziplocks, scissors, wiffle balls, K'nex - see Materials Checklist. | Dale / Tarka | 2026-07-01 | In Progress
Shipping instructions | Ship to Manassas, VA (Attn: Jill Jule). [!] Old tracker showed Pittsfield, MA - confirm correct destination. | Tarka |  | Done
Confirm receipt of materials | Confirm delivery on the GD side. | Amber Dean | ongoing | Done / Ongoing
Invoice | Invoice dated 2026-05-06 - confirm sent / paid status. Email OK to Rachel Hawthorne. | Tarka | 2026-05-06 | Verify
Reg / attendance report | Bart takes attendance and forwards sheet to Rachel. Kim confirming approach with Emil. | Bart -> Rachel |  | Open
Certificates of completion | Client confirmed: none required. | - |  | Resolved: None

## Open Items
Open Items - action list and countdown
'Days left' is live: it recalculates from today's date. Sorted by urgency.
Priority | Action | Owner | Due | Days left | Notes
CRITICAL | Confirm ship-to address is Manassas, VA (not Pittsfield, MA) | Emil | - | - | Old tracker had Pittsfield/Amber and was marked Done - verify nothing shipped to wrong site.
High | Confirm security clearance / site access | Bart / Deena | 2026-07-01 | -8 | Was due Jul 1. GDMS site needs clearance; Deena uploading material.
High | Ship printed materials (manuals + handouts) | Eric / Mimeo | 2026-08-03 | 25 | Sent to Eric to compile and ship. Target ~1 wk before event; confirm tracking.
High | Send roster and QR code to Dale | Emil | 2026-07-20 | 11 | Next dated deliverable.
Medium | Finalize attendance-reporting plan | Kim / Emil | - | - | Bart takes attendance -> forwards to Rachel. Confirm mechanics.
Medium | Confirm course-materials list complete | Eric | - | - | Detailed list incl. printing.
Medium | Confirm ship-monthly items en route | Dale / Tarka | 2026-08-03 | 25 | Ziplock bags and FFMBAs to training location.
Low | Verify invoice status | Tarka | 2026-05-06 | -64 | Invoice dated May 6 - confirm sent/paid.
Scheduled | On-site room setup | Emil / Dale | 2026-08-10 | 32 | Aug 10, 1:00-5:00 PM before Aug 11 start.
Formulas:
Days left = IF([Due]="","",[Due]-TODAY())

## Materials Checklist
Materials and Shipping Checklist
Item | Qty | Source / vendor | Status | Notes
- PRINTED (hard + soft copies) -
GD-PM Edge Student Manual | 28 | Mimeo | In Progress | PM EDGE Simulation_04-08 2026.pdf (Versatile site).
Handouts | - | Mimeo | In Progress | Incl. new Competencies 11x17 activity handout from Emil (this class forward).
Name tents | 30 | Mimeo | Done | Emil shipped in the boxed shipment.
Case studies | - | Mimeo (from Dale) | Done | Provided by Dale; reused each session.
Charts (6 different) | 7 each | United Reprographic (Seattle) | Done
- NON-PRINTED -
FFMBA books | 24 | Amazon / Tarka Corp acct | Done / Ship | Shipped to GD training address.
Plastic name-tag lanyards | - | Dale | Done | Dale manages and reuses.
Duotangs | 7-pack x12 | Bulk -> Seattle office | Done | Included in monthly boxed shipments.
Ziplock bags (9in square) | 10 | - | Ongoing | Send monthly to training location.
Scissors | - | - | Done | Dale managing.
Wiffle balls | 8 | - | Done | Dale managing.
K'nex 3in grey rods | 6 | - | Ongoing | Dale managing.
- CLIENT (GD) PROVIDES ON SITE -
Flip chart paper + markers | - | GD (Bart) | Client | Bart to ensure present.
3x3 sticky note pads | 10-12 | GD | Client
2x1 sticky note pads | 10 | GD | Client | To reference FFMBA book.
Wall-safe painter tape (Frog Tape) | - | GD | Client | To protect walls when hanging documents.
Pencils, pre-sharpened | 12-15 | GD | Client

## Budget
Budget - Expenses
Line item | Category | Amount (USD) | Notes
Mimeo - printing | Manuals & handouts | 2344.12 | Sent to Eric to compile and ship with other items.
Mimeo - shipping | Shipping | 281.93
Amazon | FFMBAs | TBD | Cost TBD - not yet recorded.
United Reprographic | Charts | TBD | Cost TBD - not yet recorded.
FedEx | Shipping | TBD | Cost TBD - not yet recorded.
Total recorded |  | 2626.05 | Sum of recorded lines only; excludes TBD items above.

## Reconciliation Notes
Reconciliation Notes - changes vs. original tracker
Client-confirmed Logistics Form (docx) treated as source of truth. Items marked [!] need a human to verify.
Field | Original tracker (xlsx) | Reconciled value (from docx) | Action
Ship-to address | GDMS, 100 Plastics Ave, Pittsfield, MA 01201 (Attn: Amber Dean) - marked Done | GD Progeny Systems, 9100 Ashton Ave, Manassas, VA 20110 (Attn: Jill Jule) | [!] VERIFY nothing shipped to Pittsfield
Daily hours | 8:00 AM - 4:00 PM EST | 8:30 AM - 4:30 PM EST | [!] Confirm correct times
Amber Dean phone | 413-449-7139 | 413-664-1210 | [!] Two numbers - verify
Venue / room | 'Training site to be confirmed' | USS Groton Conf Room, Building 3, Manassas VA | Updated - confirmed
Setup time | Not stated | Aug 10, 1:00-5:00 PM | Added
Stale template text | 'Monday, Mar 2 ... March 3 training' in classroom cell | Removed (belongs to a prior course) | Cleaned
Sheet tab name | 'BSCI PPM Sept 6' | Renamed to descriptive tabs | Cleaned
Engagement name | 'GD Program Management Sim' | 'Program Management Edge' | Standardized
Evaluation method | Not stated | GD internal system (Tarka online eval not used) | Added
Invoice contact | Not stated | Rachel Hawthorne, Rachel.Hawthorne@gd-ms.com | Added