## Dashboard
Portfolio Dashboard - live across all engagements
Recalculates from today's date. All figures roll up from the other tabs.
Engagements | Overdue tasks | Open tasks | Due next 7 days | Budget recorded
1 | 4 | 9 | 0 | 2626.05
Engagement | Client | Start | Days to start | Open tasks | Overdue | Budget | Status
Program Management Edge | General Dynamics - Progeny Systems (GDMS) | 2026-08-11 | 33 | 9 | 4 | 2626.05 | In Prep

## Engagements
Engagement Register - source of truth (one row per engagement)
Engagement ID | Name | Client | Status | Start | End | Setup | Daily Start | Daily End | Venue | Address | City | State | ZIP | Room | Instructor | Instr. Email | Instr. Phone | Support/Observer | Attendees | Pods | Roster Req. | Certificates | Evaluation | Coordinator | Site Contact | Alternate Contact | Invoice Contact | Onsite IT | Ship-To | Airports | Hotels | Notes / Flags
ENG-2026-001 | Program Management Edge | General Dynamics - Progeny Systems (GDMS) | In Prep | 2026-08-11 | 2026-08-20 | 2026-08-10 | 8:30 AM | 4:30 PM | GD Progeny Systems | 9100 Ashton Ave | Manassas | VA | 20110 | USS Groton Conf Room, Bldg 3 | Dr. Dale Christenson | dale@pmcoe.ca | 250-217-5362 | Emil Tarka | 24 | 6 | No | No | GD internal system | Bart Turrano ¦ Bart.Turrano@gd-ms.com | Jill Jule ¦ Jill.Jule@gd-ms.com ¦ (571) 370-7495 | Amber Dean ¦ Amber.Dean@gd-ms.com ¦ 413-664-1210 | Rachel Hawthorne ¦ Rachel.Hawthorne@gd-ms.com | Brandon Dowdy | Attn: Jill Jule, 9100 Ashton Ave, Manassas VA 20110 | IAD or DCA | Residence Inn (10m) ¦ Courtyard (15m) ¦ Westfields Marriott (20m) | [!] Verify ship-to (old file said Pittsfield); hours 8:30-4:30; confirm security clearance

## Tasks
Tasks - all engagements (drives reminders & portfolio rollups)
Engagement ID | Task | Owner | Due | Status | Days Left | Open? | Overdue? | Notes
ENG-2026-001 | Instructor confirmed | Tarka |  | Confirmed |  | 0 | 0 | Dale leads; Emil observes.
ENG-2026-001 | Onsite / in-person class | - |  | Confirmed |  | 0 | 0 | Manassas VA, Bldg 3.
ENG-2026-001 | Request roster / logistics | Emil | 2026-06-15 | Done | -24 | 0 | 0 | Logistics sheet to Bart.
ENG-2026-001 | Completed logistics form | Emil | 2026-06-20 | Done | -19 | 0 | 0 | Form COMPLETE; sent to Dale.
ENG-2026-001 | Roster & QR code | Emil | 2026-07-20 | Open | 11 | 1 | 0 | Send roster to Dale.
ENG-2026-001 | Course list | Eric |  | In Progress |  | 1 | 0 | Detailed materials list incl. printing.
ENG-2026-001 | Classroom access / clearance | Bart / Emil | 2026-07-01 | Confirm | -8 | 1 | 1 | GDMS site security clearance.
ENG-2026-001 | Classroom arrangement | Emil / Dale | 2026-08-10 | Scheduled | 32 | 1 | 0 | 6 pods of 4; set up Aug 10.
ENG-2026-001 | Security access upload | Deena |  | Confirm |  | 1 | 0 | Deena uploading material.
ENG-2026-001 | Course materials (printed) | Eric / Mimeo | 2026-07-01 | In Progress | -8 | 1 | 1 | Manuals 28 + handouts; ship.
ENG-2026-001 | Materials (non-printed) | Dale / Tarka | 2026-07-01 | In Progress | -8 | 1 | 1 | FFMBAs, ziplocks, etc.
ENG-2026-001 | Shipping instructions | Tarka |  | Done |  | 0 | 0 | [!] Ship to Manassas, not Pittsfield.
ENG-2026-001 | Confirm receipt of materials | Amber Dean |  | Done / Ongoing |  | 0 | 0 | GD-side delivery.
ENG-2026-001 | Invoice | Tarka | 2026-05-06 | Verify | -64 | 1 | 1 | Confirm sent/paid; email Rachel.
ENG-2026-001 | Reg / attendance report | Bart / Rachel |  | Open |  | 1 | 0 | Bart -> Rachel.
ENG-2026-001 | Certificates of completion | - |  | Resolved: None |  | 0 | 0 | Client: none required.
Formulas:
Days Left = IF([Due]="","",[Due]-TODAY())
Overdue? = IF(AND(ISNUMBER([Due]),[Due]<TODAY(),[Open?]=1),1,0)

## Materials
Materials - per engagement
Engagement ID | Item | Qty | Vendor | Type | Status | Notes
ENG-2026-001 | GD-PM Edge Student Manual | 28 | Mimeo | Printed | In Progress | PM EDGE Simulation_04-08 2026.pdf
ENG-2026-001 | Handouts | - | Mimeo | Printed | In Progress | Incl. Competencies 11x17 handout.
ENG-2026-001 | Name tents | 30 | Mimeo | Printed | Done | Shipped in boxed shipment.
ENG-2026-001 | Case studies | - | Mimeo (Dale) | Printed | Done | Reused each session.
ENG-2026-001 | Charts (6 diff.) | 7 each | United Reprographic | Printed | Done | Seattle printer.
ENG-2026-001 | FFMBA books | 24 | Amazon / Tarka Corp | Non-printed | Done | Shipped to training address.
ENG-2026-001 | Name-tag lanyards | - | Dale | Non-printed | Done | Reused.
ENG-2026-001 | Duotangs | 7-pk x12 | Bulk / Seattle | Non-printed | Done | Monthly shipments.
ENG-2026-001 | Ziplock bags 9in | 10 | - | Non-printed | Ongoing | Monthly.
ENG-2026-001 | Scissors | - | Dale | Non-printed | Done
ENG-2026-001 | Wiffle balls | 8 | Dale | Non-printed | Done
ENG-2026-001 | K'nex 3in rods | 6 | Dale | Non-printed | Ongoing
ENG-2026-001 | Flip chart + markers | - | GD (Bart) | Client | Client | On site.
ENG-2026-001 | Sticky notes 3x3 / 2x1 | 10-12 / 10 | GD | Client | Client
ENG-2026-001 | Frog painter tape | - | GD | Client | Client | Protect walls.
ENG-2026-001 | Pencils | 12-15 | GD | Client | Client | Pre-sharpened.

## Budget
Budget - expenses per engagement
Engagement ID | Line item | Category | Amount (USD) | Status | Notes
ENG-2026-001 | Mimeo - printing | 2344.12 | 2344.12 | Recorded | Sent to Eric to compile/ship.
ENG-2026-001 | Mimeo - shipping | 281.93 | 281.93 | Recorded
ENG-2026-001 | Amazon |  | TBD | TBD | Cost not yet recorded.
ENG-2026-001 | United Reprographic |  | TBD | TBD | Cost not yet recorded.
ENG-2026-001 | FedEx |  | TBD | TBD | Cost not yet recorded.

## TaskTemplate
Task Template - standard tasks applied to every new engagement
Task | Owner (role) | Offset (days from Start) | Notes
Send logistics form to client coordinator | Coordinator | -56 | Request roster & site details.
Receive completed logistics form | Coordinator | -49 | Confirm venue, AV, shipping, contacts.
Confirm venue & security/site access | Coordinator | -42 | Clearance if required.
Send roster & QR code to instructor | Coordinator | -21
Order printed materials (manuals, handouts) | Materials lead | -21 | Mimeo.
Order charts | Materials lead | -21 | United Reprographic.
Ship materials to site | Materials lead | -10 | Confirm tracking.
Confirm receipt of materials | Site contact | -5
On-site room setup | Instructor | -1 | Pods, AV check.
Take attendance / reporting | Coordinator | 0 | Forward to invoicing.
Issue invoice | Finance | 5 | Per client instructions.
Certificates decision | Coordinator | -14 | Confirm Yes/No with client.

## Lists
Lists (validation)
Engagement Status | Task Status | Material Type
Planning | Open | Printed
In Prep | In Progress | Non-printed
Confirmed | Confirm | Client
Delivered | Verify
Closed | Scheduled
Done
Confirmed
Done / Ongoing
Resolved: None